## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US01 | As a developer, I want to design a Maven-based multi-module project so dependency management and modularity are streamlined. | MUST HAVE | Maven & Jakarta Libraries | Manogna | 3 - Completed
Sprint 1 | Sprint 1 | US02 | As a DevOps engineer, I want automated setup for Tomcat server and deployment pipelines, so application deployment is reliable and fast. | MUST HAVE | Tomcat Server & CI/CD | Manogna | 3 - Completed
Sprint 1 | Sprint 1 | US03 | As a backend developer, I need robust JDBC configuration and secure DB credentials management for banking data access. | MUST HAVE | MySQL Database | Manogna | 3 - Completed
Sprint 2 | Sprint 2 | US04 | As a user, I want self-registration so I can open a banking account and access digital services securely. | MUST HAVE | User Registration & DAO | Manogna | 3 - Completed
Sprint 2 | Sprint 2 | US05 | As a user, I want a secure login system with credential validation and session handling to protect my account. | MUST HAVE | Login Module | Manogna | 3 - Completed
Sprint 2 | Sprint 2 | US06 | As a user, I need to view my account balance in real-time from web or mobile interface for better financial planning. | SHOULD HAVE | Account Service & DAO | Manogna | 3 - Completed
Sprint 3 | Sprint 3 | US07 | As a customer, I want to transfer funds instantly to another account and receive a transaction confirmation. | MUST HAVE | Transaction Service | Manogna | 3 - Completed
Sprint 3 | Sprint 3 | US08 | As a user, I wish to view my detailed transaction history for personal auditing. | SHOULD HAVE | Transaction History Module | Manogna | 3 - Completed
Sprint 3 | Sprint 3 | US09 | As a developer, I must add centralized exception handling and comprehensive logging to all backend modules. | MUST HAVE | Exception Module & Logger | Manogna | 3 - Completed
Sprint 4 | Sprint 4 | US10 | As a developer, I want robust REST APIs for integration with mobile/web clients and for partner banking usage. | COULD HAVE | REST API Service Layer | Manogna | 3 - Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 85 | 49 | 32 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US01 | T01 | Create Maven project and configure dependencies (Jakarta EE, JDBC, MySQL Connector) | 9/15/2025 | 15/Sep/25 | Manogna | Setup | Completed | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US01 | T02 | Configure Tomcat 11 server and test initial deployment | 9/16/2025 | 16/Sep/25 | Manogna | Setup | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US03 | T03 | Create MySQL database schema for accounts & transactions | 9/17/2025 | 17/Sep/25 | Manogna | Database | Completed | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US03 | T04 | Implement DBConnectionUtil class for JDBC connectivity | 9/18/2025 | 18/Sep/25 | Manogna | Development | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US04 | T05 | Create DAO classes for User and Account entities | 9/20/2025 | 20/Sep/25 | Manogna | Development | Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US04 | T06 | Write SQL queries for insert, update and fetch operations | 9/21/2025 | 22-Sep-25 | Manogna | Database | Completed | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US05 | T07 | Develop RegistrationServlet and LoginServlet controllers | 9/23/2025 | 23-Sep-25 | Manogna | Development | Completed | 5 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US05 | T08 | Implement password encryption and validation logic | 9/25/2025 | 25-Sep-25 | Manogna | Security | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US06 | T09 | Test DAO and Servlet integration with database | 9/26/2025 | 26-Sep-25 | Manogna | Testing | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US07 | T10 | Create REST Controllers for User and Account CRUD | 9/27/2025 | 27-Sep-25 | Manogna | API Development | Completed | 5 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US08 | T11 | Configure centralized Exception Handling and Logging | 9/28/2025 | 28-Sep-25 | Manogna | Maintainence | Completed | 5 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US09 | T12 | Test backend using Postman for all endpoints | 9/29/2025 | 29-Sep-25 | Manogna | Testing | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US10 | T13 | Initialize React project and install dependencies | 9/30/2025 | 30-Sep-25 | Manogna | Frontend Setup | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US11 | T14 | Setup React Router and project structure | 10/1/2025 | 1-Oct-25 | Manogna | Frontend Setup | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US12 | T15 | Create reusable components (Navbar, Sidebar, Tabs) | 10/2/2025 | 2-Oct-25 | Manogna | Frontend Dev | Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US13 | T16 | Develop AccountTable & TransactionTable components | 10/3/2025 | 3-Oct-25 | Manogna | Frontend Dev | Completed | 7 | 2 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US14 | T17 | Implement CreateAccount and Transaction forms | 10/4/2025 | 4-Oct-25 | Manogna | Frontend Dev | Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US15 | T18 | Integrate frontend with backend REST APIs | 10/5/2025 | 5-Oct-25 | Manogna | Integration | Completed | 8 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US16 | T19 | Perform end-to-end testing (Postman + UI testing) | 10/6/2025 | 6-Oct-25 | Manogna | Testing | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | DAY1 | Struggled with Maven profile conflicts during library integration. | Resolved by adjusting Maven settings and confirming dependency versions.
Sprint 1 | DAY3 | Annotations missing on REST services, resulting in unresponsive endpoints. | Checked all controller classes and re-added necessary annotations for activation.
Sprint 1 | DAY5 | Backend failed to establish initial database connectivity. | Verified driver installation and managed connection pooling configuration.
Sprint 2 | DAY4 | Unexpected frontend request failures due to incorrect CORS settings. | Revised application config to explicitly permit browser origins as needed.
Sprint 2 | DAY5 | Issues encountered in date formatting for API responses. | Injected custom serializers and validated ISO date format throughout modules.
Sprint 2 | DAY3 | Lost track of schema migration updates during backend CRUD expansion. | Performed full schema sync, retested updated APIs and executed sample transactions.
Sprint 3 | DAY1 | Mismatch in user profile fields between client and server code. | Aligned DTO structures and harmonized API payload mapping.
Sprint 3 | DAY5 | Persisting React errors slowed new feature deployment. | Refactored error handlers, batch resolved outstanding frontend bugs.
Sprint 4 | DAY2 | After-deletion info not showing instantly on frontend. | Linked event responses with UI refresh; tested multiple delete scenarios.
Sprint 4 | DAY3 | Build pipeline failed due to Tomcat deployment misstep. | Fixed path references and re-configured build automation for smoother releases.
Sprint 4 | DAY4 | Environment file was not being read during frontend startup. | Moved config variables, updated build scripts and verified local/startup behavior.
Sprint 4 | DAY5 | Final documentation review pending ahead of sprint closeout. | Compiled user guides, API spec, and validated test procedures in one go.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-09-15 | 2025-09-20 | Manogna | Review security checklists and code scans during initial setup. | Stop using default configurations without validation. | Continue documenting all environment changes. | Integrated automated vulnerability scanning and enforced configuration review before deployment.
2 | Sprint 1 | 2025-09-15 | 2025-09-20 | Manogna | Add API response validation in Postman tests. | Stop merging code without successful endpoint tests. | Continue pairing backend and frontend testing. | Expanded Postman test suite and set up merge checks for API responses.
3 | Sprint 2 | 2025-09-21 | 2025-09-25 | Manogna | Refactor DAO layer with better abstraction for test isolation. | Stop keeping business logic in JDBC utility classes. | Continue modularizing persistency methods. | Designed repository pattern for reusability and improved DAO testability.
4 | Sprint 2 | 2025-09-21 | 2025-09-25 | Manogna | Ensure audit logging for all transaction processes. | Stop overlooking exception trace logs during debugging. | Continue using global error handlers. | Enabled audit trail feature for sensitive operations and reviewed exception handling coverage.
5 | Sprint 3 | 2025-09-26 | 2025-09-30 | Manogna | Create and use reusable frontend state management hooks. | Stop duplicating stateful logic across components. | Continue leveraging React context for shared data. | Encapsulated API hooks, reduced complexity, and improved maintainability in React.
6 | Sprint 3 | 2025-09-26 | 2025-09-30 | Manogna | Increase API versioning practices for upcoming features. | Stop making breaking backend changes without versioning. | Continue regression testing across API versions. | Introduced API versioning policy and applied backward compatible updates to endpoints.
7 | Sprint 4 | 2025-10-01 | 2025-11-05 | Manogna | Use continuous integration to trigger build/test pipelines automatically. | Stop ignoring failed jobs on CI/CD dashboard. | Continue reviewing build logs routinely. | Linked GitHub Actions with CI pipelines and configured alerts for test failures.