## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Manogna | 2025-09-16 | Build failed due to conflicting Maven plugin versions | Sprint 1 | Manogna | Standards | Aligned plugin versions and resolved dependency tree | 2025-09-16 | Closed | Build Verified
2 | Manogna | 2025-09-18 | JDBC URL typo causing database authentication error | Sprint 1 | Manogna | Logical | Corrected connection string format | 2025-09-18 | Closed | DB Connection OK
3 | Manogna | 2025-09-19 | Tomcat port blocked by another process | Sprint 1 | Manogna | Logical | Changed server port in config | 2025-09-19 | Closed | Server Running
4 | Manogna | 2025-09-22 | Resource leaks in DAO when fetching transaction list | Sprint 1 | Manogna | Maintainability | Refactored using try-with-resources | 2025-09-22 | Closed | No Leak Found
5 | Manogna | 2025-09-24 | Duplicate entries on customer sign-up | Sprint 2 | Manogna | Logical | Added pre-insert uniqueness validation | 2025-09-25 | Closed | Verified Uniqueness
6 | Manogna | 2025-09-27 | NPE triggered by referencing non-existent Account ID | Sprint 2 | Manogna | Logical | Inserted null-safety checks in service class | 2025-09-27 | Closed | Test Passed
7 | Manogna | 2025-10-01 | API response data mismatches with frontend component expectations | Sprint 2 | Manogna | Standards | Synced DTO formats front-and-back | 2025-10-01 | Closed | UI Data Synced
8 | Manogna | 2025-10-03 | Slow login performance under test environment | Sprint 2 | Manogna | Logical | Profiled queries, indexed relevant columns | 2025-10-03 | Closed | Improved Speed
9 | Manogna | 2025-10-05 | Transaction service inconsistent error messaging | Sprint 3 | Manogna | Maintainability | Standardized error objects in REST API | 2025-10-05 | Closed | Errors Consistent
10 | Manogna | 2025-10-06 | Logging not enabled for transfer API | Sprint 3 | Manogna | Maintainability | Set up logging to file and console | 2025-10-06 | Closed | Logs Visible
11 | Manogna | 2025-10-08 | Transaction rejecting valid sender due to outdated balance cache | Sprint 3 | Manogna | Logical | Updated balance cache logic, enforced flush | 2025-10-08 | Closed | Verified

## Sheet2
Logical
User Interface
Maintainability
Standards
Others